## ProjectSchedule
Erskine Park Landfill - GCS Installation
Cleanaway |  | Project Start: | 2020-05-01
Run Energy Pty Ltd |  | Today: | 2020-05-06
Start date is an estimate only |  | Display Week: | 1 |  |  | 2020-04-27 | [6 empty] | 2020-05-04 | [6 empty] | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | 2020-06-01 | [6 empty] | 2020-06-08 | [6 empty] | 2020-06-15 | [6 empty] | 2020-06-22 | [6 empty] | 2020-06-29 | [6 empty] | 2020-07-06 | [6 empty] | 2020-07-13 | [6 empty] | 2020-07-20
 | time axis 2020-04-27 to 2020-07-26
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-04-27 to 2020-07-26
Preliminaries
Awarded tender |  |  | 2020-05-01 | 2020-05-01 | 1
Procurement and delivery of materials |  |  | 2020-05-01 | 2020-05-01
Submission of HSE documents |  |  | 2020-05-02 | 2020-05-02
Submission of CEMP |  |  | 2020-05-02 | 2020-05-02
Survey of well locations |  |  | 2020-05-15 | 2020-05-15
Commencement
Pre start meeting on site and mobilise (2men) |  |  | 2020-05-15 | 2020-05-15
Butt weld well pipes (2 men) |  |  | 2020-05-16 | 2020-05-17
Construct pads for drill rig (2 men) |  |  | 2020-05-16 | 2020-05-17
Drill and install well x 12 (crew of 4) |  |  | 2020-05-19 | 2020-05-28
Trench, weld and lay 145m x 200 mm header line (4 man crew) |  |  | 2020-05-29 | 2020-05-30
Trench, weld and lay 480m x 160 mm header line (4 man crew) |  |  | 2020-06-01 | 2020-06-06
Trench, weld and lay 385m x 90 mm header line (4 man crew) |  |  | 2020-06-08 | 2020-06-10
Install 6 x barometric traps (crew of 4) |  |  | 2020-06-11 | 2020-06-12
Demobilise and survey (crew of 2) |  |  | 2020-06-13 | 2020-06-13
2018-01-13
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.